## A3 Verkefni - Sniðmát (2)
Title: Lyfjagjafir Parkinsonsjúklinga við bráðar innlagnir á LSH | Date: 30.3.2021 | Project team: Snædís Jónsdóttir, Marianne E. Klinke, Þorbjörg Sóley Ingadóttir, Elín Ingibjörg Jacobsen og Bylgja Kærnested
Supervisor: Amelia Samuels |  |  |  | Project lead (resident): | Snædís Jónsdóttir
Aim statement (What are we trying to accomplish?) |  | 1 | Meaures (How will we know a change is an improvement?) (list measures) |  |  |  |  | 4
Abrupt suspension of PD med. can cause discomfort and increase physical og mental decline. There is also a risk for parkinsonism-hyperpyrexia syndrome and dopamine withdrawal symptoms. I want to increase the number of patients with PD that recieve their first PD medication dose </=1 hour from their schedule after being admitted acutely to 14EG, from 38,7% and 20% in 13EG of Landspítali to 70% by January 2022. Also that the median hours of delay of the first recieved dose lowers from 1,3 (14EG) and 1,8 hours (13EG) to <1 hour. |  |  | i. Time from the first given PD medication dose after an acute admission to 14EG and 13EG compared to when the patient should have received the first dose, deviation in min/hours. ii. Proportion of patients that receive their first PD medication dose </=1 hour from the correct medicatoin time after an acute admission to 14EG og 13EG
What process(es) are we trying to improve? (process map) |  | 2 | Action plan |  |  |  |  | 5
|  |  | Action |  |  | By whom | Date | Status
|  |  | Data: PD patients (G20) at the ER ´19/´20, why they came, where admitted |  |  | SJ | 17/3´21 | Lokið
|  |  | Talk to Elísabet Guðmundsdóttir regarding the QI project |  |  | SJ/JHH | 26/3 ´21 | Lokið
|  |  | Data: patients on L-dopa in LSH ´19/´20, day of admission, time of first dose |  |  | SJ | 26/3 ´21 | Lokið
|  |  | Analyze data, decide what department to work with |  |  | SJ | 14/4 ´21 | Lokið
|  |  | Analyze data, look up patients and compare medication time |  |  | SJ | 12/5 ´21 | Lokið
|  |  | Meeting with Bylgja head of cardio (14EG) |  |  | SJ | 23/9 ´21 | Lokið
|  |  | Medication arrive at 14EG |  |  | SJ/BK | 11/10´21 | Lokið
|  |  | E-mail to head of inpatient wards at Hb, ICU, 11EG, 12G, 13G, 21A, 12E |  |  | SJ | 12/10´21 | Lokið
|  |  | Put stickers in medication cabinets in Hb to point to 14EG |  |  | SJ | 14/10´21 | Lokið
|  |  | Information about the QI project put on Workplace |  |  | SJ | 20/10 ´21 | Lokið
|  |  | Education about the project, part of starfsþróunarár |  |  | SJ | 21/10 21 | Lokið
|  |  | Meeting with Parkinsonsamtökin |  |  | SJ | 15/11 21 | Lokið
|  |  | Meeting with clinical pharmacists |  |  | SJ/JHH | 19/11 21 | Lokið
|  |  | Education about the project, nurses in diploma and masters (HÍ) |  |  | SJ | 21/11 21 | Lokið
|  |  | Education about the project, 14EG |  |  | SJ | 24/11 ´21 | Lokið
|  |  | Analyze data, check for improvement 14EG/13EG okt-des ´21 |  |  | SJ | 17/12 ´21 | Lokið
|  |  | Add Stalevo to medication supplies in 14EG |  |  | SJ/EIJ | 4/1 ´22 | Lokið
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  | 3 | Results (Run Chart) |  |  |  |  | 6
5 Why´s: What is the problem - PD patients often receive their medication late/ not at all. Why does this occur - Can be some time waiting for the doctors to ord. the medication Why does this occur - Sometimes patients don´t bring information about their med. and information is not easily accessible Why does this occur - Patients don´t always get information about their medications on paper (lyfjakort) Why does this occur - Information about medication, doses and timings often not accessible 5 why´s What is the problem - PD patients often have to wait a long time before receiving their medication Why does this occur - The medications arent available at the departments Why does this occur - PD med. arent available on all departments, many different medications, doses, often patients dont bring their medication with them to the hospital Why does this occur - Cost, expiration, patients are admitted acutely Why does this occur - root cause. Medication unaccessible 5 why´s What is the problem - PD patients often receive their medication late/ not at all Why does this occur - Patient is unable to swallow the medications Why does this occur - impairment of consciousness, dysphagia, fasting, GI problems Why does this occur - severe illness Why does this occur - root cause need to find a different administration path to give the medications
|  |  | Implementation, follow up and lessons learned |  |  |  |  | 7
Better access to medications together with education about the importance of correct PD medication administration
can give effective results
Continuing work with PD patients – medication lists/bring their med. to hospital
Talking to patients in the outpatient clinic and work with Parkinsonsamtökin
Multidisciplinary approach - work with residents - prioritize PD med. ord/ correct for late/missed doses
Article in Tímarit hjúkrunarfræðinga, poster in nurses week

## Example
Title: Improving medication safety at discharge from hospital | Date: | 2021-01-19 | Project team: Anna Björg Jónsdóttir, Geriatrics Specialist Dagdeild (Lead), Helga Kristinsdóttir (clinical pharmacist), Hlynnur Grímsson (GP resident), Bryndís Guðjónsdóttir (Nurse, Dagdeild)
Owner: Transitions of Care & Polypharmacy Workstream (WHO Medication Without Harm) |  |  |  |  | Project Manager: Amelia Samuel
Aim statement (What are we trying to accomplish?) |  |  | 1 | Meaures (How will we know a change is an improvement?) (list measures) |  |  |  | 4
There is lack of standadisation and clear processes relating to medication review and information from admission to Dagdeild, Landakot through to discharge. It is difficult to get correct information at the start and we can't be sure that the information is accurate. At discharge, we don't have closed loop communication with the GP, home care and dispensaries. We run into problems when there are medication changes. Patients may not be getting clear and understandable information about what medications they are taking, especially high risk medications. We aim to make improvements in 5 stages: 1. To improve the quality of medicines reconciliation at admission to the Dagdeild for at least 80% of patients from level 1 (low quality) to 3 (high quality) by April 2021. After which time, we will test similar solutions in 2 or 3 other departments and if ready, scale up across Landspítali and then other healthcare providers. Following stages are: 2. structured medication review during the patient's stay, 3. good quality medicines reconciliation at discharge, 4. better communication with patients about their medications at discharge and 5. better communication with GPs. |  |  |  | Stage 1: Improving medicines reconciliation at admission - Quality of medicines reconciliation at admission (rate from 0 - 3)
|  |  |  | Action plan |  |  |  | 5
|  |  |  | Action |  | By whom | Date | Status
|  |  |  | Implement PDSA 1 |  | ABJ | 2021-11-30 | complete
What process(es) are we trying to improve? (process map) |  |  | 2 | Discuss learning from PDSA 1 |  | ABJ / AS | 2021-12-09 | complete
Stage 1: improving medicines reconciliation at admission |  |  |  | Discuss with junior doctor ideas and learning from PDSA 1 |  | AS | 2021-12-15 | complete
|  |  |  | Plan what to do for PDSA 2 |  | ABJ / AS | 2021-12-20 | complete
|  |  |  | Design checklist template to guide documentation (for PDSA 2) |  | ABJ / HK | 2021-12-23 | complete
|  |  |  | Check with HUT possibility of developing template on Heilsugátt for PDSA 2 |  | AS | 2021-01-10 | complete
|  |  |  | Meet secretaries to discuss how to get more patients to bring their medications with them |  | AS | 2021-01-18 | complete
|  |  |  | Set date for PDSA 2 to go live (request sent to IT on 18.01) |  | ABJ/AS | 2021-01-15 | In progress
|  |  |  | PDSA 3 recommended - set date. |  | ABJ/AS/Guðlaug | 2021-01-22 | In progress
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  |  | 3 | Results (Run Chart) |  |  |  | 6
Stage 1: improving medicines reconciliation at admission 1) Checklist to improve quality of medicines reconciliation at admission. 2) Strategies to improve patients bringing their medications with them to their appointments.
|  |  |  | Implementation, follow up and lessons learned |  |  |  | 7
Learnings:
- PDSA 1 taught us that the checklist as a poster is not an effective way to promote change in behaviour and doctors are not routinely documenting when they have obtained information from >1 source. It also taught us that the quality of medication reconciliation is better when the patient brings their medication with them.
- PDSA 2 will be a template of the checklist programmed into Saga to prompt the doctor to use it and document the outcome of the consultation with the patient in a structured way.
- PDSA 3 will be to inform all patients in the Dagdeild and göngudeild on the phone 1 day before their appointments to bring their medications, instructions about what to bring and emphasise importance of this.