## A3 Verkefni - Sniðmát (2)
Title: | Date: | Project team:
Supervisor: |  |  |  | Project lead (resident):
Aim statement (What are we trying to accomplish?) |  | 1 | Meaures (How will we know a change is an improvement?) (list measures) |  |  |  | 4
What process(es) are we trying to improve? (process map) |  | 2 | Action plan |  |  |  | 5
|  |  | Action |  | By whom | Date | Status
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  | 3 | Results (Run Chart) |  |  |  | 6
|  |  | Implementation, follow up and lessons learned |  |  |  | 7

## EXAMPLE
Title: Improving labelling of PAP smear samples | Date: | 2023-06-19 | Project team: Hulda Þorsteinsdóttir, Sigrún Perla Böðvarsdóttir, Ásdís Larsen, SKS, HUT
Supervisor: Sigrún Perla Böðvarsdóttir |  |  |  |  | Project lead (resident): | Hulda Þorteinsdóttir
Aim statement (What are we trying to accomplish?) |  |  | 1 | Meaures (How will we know a change is an improvement?) (list measures) |  |  |  | 4
Processing of PAP smear samples before sending them from Gyn department at Landspitali Hospital has not been meeting the standards set from the Coordination center of cancer screening in Iceland (SKS), both in terms of labelling and the requests that need to be sent with them. The goal of this project is to simplify the process for labelling PAP smear samples so that less than 5% of samples sent from Landspitali will be incorrectly labeled. Simplified process will both save time for healthcare workers and increase quality and safety in sample processing which will result in increased patient safety. |  |  |  | Process measure: PAP smears are sent weekly from the Gyn department at Landspitali Hospital. Number of incorrectly labelled PAP smears were collected manually by weekly counting before they were sent of (checking label positions, if all info was included and matched with request on the computer). Other possible measures: Outcome/efficiency measures: Number of patients having repeat smears (not collected, not feasible within timeframe of project). Number of steps / amount of time taken to label PAP smears (not collected, not feasible). Balancing measures: Staff satisfaction (not collected, not feasible)
What process(es) are we trying to improve? (process map) |  |  | 2 | Action plan |  |  |  | 5
|  |  |  | Action |  | By whom | Date | Status
|  |  |  | Process MAP, Fish analysis |  | HÞ | 2022-10-20 | Finished
|  |  |  | Team meeting for planning project |  | HÞ/SPB | 2022-10-25 | Finished
|  |  |  | Baseline measuring quality of labelling |  | HÞ | 7-21.11.22 | Finished
|  |  |  | Contact (meeting, email) with SKS about simplified labelling demands |  | HÞ/SPB/ÁIÁ | nov '22 | Finished
|  |  |  | Meeting with head of tech department at Landspitali (HUT) |  | HÞ/BJ | 2022-11-10 | Finished
|  |  |  | First result put in the run chart |  | HÞ | 2023-11-15 | Finished
|  |  |  | Project request to HUT for analysis and tech improvements |  | BJ/HÞ | 2022-11-18 | Finished
|  |  |  | Team meeting |  | HÞ/SPB | 2022-12-05 | Finished
|  |  |  | Simplified labelling demands from SKS announced |  | SKS/ÁIÁ | 2022-12-18 | Finished
|  |  |  | PDSA1: Presentation for Gyn department about simplified labelling |  | HÞ | 2023-01-19 | Finished
|  |  |  | Measurement of effect of PDSA1 |  | HÞ | jan-feb '23 | Finished
|  |  |  | Second results put in the run chart |  | HÞ | 2023-02-20 | Finished
|  |  |  | PDSA2: with flowchart posters and Workplace reminder |  | HÞ | 2023-02-22 | Finished
|  |  |  | Measurement of effect of PDSA 2 |  | HÞ | feb-mar '23 | Finished
|  |  |  | Third results set up as run chart |  | HÞ | 2023-04-17 | Finished
|  |  |  | Introduction of the outcomes of quality improvement project |  | HÞ | 2023-06-02 | Finished
|  |  |  | Meeting with HUT and trial version of new request system in Heilsugátt released |  | HÞ | 2023-06-19 | Finished
What change can we make that will result in improvement? (5 Why's/Fishbone diagram & change ideas) |  |  | 3 | Results (Run Chart) |  |  |  | 6
|  |  |  | Implementation, follow up and lessons learned |  |  |  | 7
By reducing the number of labels that were needed to put on each sample from orignally 3-4 labels to 2 and making more clear instructions to the staff (PDSA1), it was possible to significantly reduce the number of incorrectly labelled samples. Additional reminders for the staff on how to follow the new process were also required (PDSA2). The original plan for PDSA2 was a new request system but the process with HUT took too long time for the time frame of the QI project. The process was still too complicated, with the request that had to be sent and label printing being separate steps and still the possibilities to print a label with incorrect information which made a risk of relapsing back to higher percentage of incorrectly labelled samples. Kept on working with HUT after QI project outcomes were introduced and in June/July '23 a new request system in Heilsugátt was released where it is possible to send a request and print label with all the information in the same step.